## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
User Story #1: Guest Checkout | 8 |  | 23 | 8 | 6 | 2 | 4 | 3 | 0 | To Do
Create guest flag in customer model (is_guest) | 2 | Ayden Hocking | 7 | 5 | 2 | 0 | 0 | 0 | 0 | Done | 0
Modify order controller to support guest users | 3 | Ayden Hocking | 8 | 2 | 2 | 2 | 1 | 1 | 0 | Done | 0
Update endpoint logic for guest validation | 2 | Ayden Hocking | 6 | 1 | 2 | 0 | 2 | 1 | 0 | Done | 0
Test guest checkout flow | 1 | Ayden Hocking | 2 | 0 | 0 | 0 | 1 | 1 | 0 | Done | 1
User Story #2: Detailed Menu Exploration | 5 |  | 19 | 6 | 4 | 3 | 3 | 3 | 0 | To Do
Add filtering logic in menuitem controller | 2 | Deeksha Marpadaga | 10 | 5 | 2 | 2 | 1 | 0 | 0 | Done | 0
Add query parameters (e.g category, price, etc) | 1 | Deeksha Marpadaga | 4 | 1 | 1 | 1 | 1 | 0 | 0 | Done | 0
Update API for menu filter | 1 | Deeksha Marpadaga | 3 | 0 | 1 | 0 | 1 | 1 | 0 | Done | 0
Test and validate filter responses | 1 | Deeksha Marpadaga | 2 | 0 | 0 | 0 | 0 | 2 | 0 | Done | 1
User Story #3: Payment Processing | 5 |  | 13 | 6 | 3 | 4 | 0 | 0 | 0 | To Do
Implement payment endpoint in controller | 2 | Group 15 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | Done | 0
Add validation for payments | 2 | Group 15 | 6 | 0 | 3 | 3 | 0 | 0 | 0 | Done | 0
Test for payment functionality | 1 | Group 15 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Done | 1
User Story #4: Apply Promo Code to Orders | 5 |  | 19 | 2 | 4 | 5 | 5 | 2 | 1 | To Do
Build promo code schema and database entry | 1.5 | Divine Mobote | 7 | 1 | 2 | 3 | 1 | 0 | 0 | Done | 0
Add promo code validation in promo controller | 2 | Divine Mobote | 5 | 1 | 2 | 1 | 1 | 0 | 0 | Done | 0
Link promo code application to order logic | 0.5 | Divine Mobote | 5 | 0 | 0 | 1 | 3 | 1 | 0 | Done | 0
Test valid and invalid promo code scenarios | 1 | Divine Mobote | 2 | 0 | 0 | 0 | 0 | 1 | 1 | Done | 2
User Story #5: View and Track Orders | 8 |  | 4 | 3 | 1 | 0 | 0 | 0 | 0 | To Do
Create /orders/ {id} endpoint for status checking / order type | 8 | Group 15 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | Done | 1
User Story #6: Customer feedback and rating | 3 |  | 8 | 0 | 0 | 0 | 3 | 3 | 2 | To Do
Create /reviews/ {id} endpoint for order evaluation | 3 | Group 15 | 8 | 0 | 0 | 0 | 3 | 3 | 2 | Done | 2
User Story #7: Collect and use data | 8 |  | 14 | 0 | 0 | 3 | 4 | 4 | 3 | To Do
Add revenue calculation | 4 | Ayden Hocking | 8 | 0 | 0 | 2 | 2 | 2 | 2 | Done | 2
Make filtering for reviews | 4 | Divine Mobote | 6 | 0 | 0 | 1 | 2 | 2 | 1 | Done | 2
TOTAL |  |  | 100 | 25 | 18 | 17 | 19 | 15 | 6